## Business Case
Business Case: Business_Case
Initiative Purpose / Description: | Problem Statement: Manual threat intelligence processing is time-consuming inconsistent and unable to keep pace with threat volume creating critical detection gaps Solution Overview: Leverage locally-deployed LLM to process unstructured threat data at scale with 95% accuracy maintaining data sovereignty and regulatory compliance
Initiative Outcomes
Category | Item | Description | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Owner
Success_Metrics | Threat_Processing_Volume | 150 feeds (40% coverage) baseline | 250 feeds (65%) | 350 feeds (90%) | 375 feeds (100%) | 375 feeds (100%) | Intelligence Lead
Success_Metrics | Threat_Extraction_Accuracy | 75% manual baseline | 90% | 93% | 95% | 96% | AI Engineering Lead
Success_Metrics | Mean_Time_Threat_Identification | 4.2 hours baseline | 2.5 hours | 1.8 hours | 1.2 hours | 45 minutes | SOC Manager
Success_Metrics | False_Positive_Rate | 25% baseline | 15% | 12% | 10% | 8% | Data Quality Lead
Success_Metrics | Analyst_Time_Saved | 0 hours/week baseline | 40 hours/week | 80 hours/week | 120 hours/week | 150 hours/week | Operations Manager
Success_Metrics | Compliance_Audit_Score | 75% baseline | 85% | 90% | 92% | 95% | Compliance Officer
Success_Metrics | Repository_Query_Performance | 8 seconds baseline | 5 seconds | 3 seconds | 2 seconds | <2 seconds | Platform Engineer
Success_Metrics | LLM_Processing_Availability | nan | 95% | 97% | 99% | 99.50% | Infrastructure Lead
Objectives & Key Results (OKRs)
Quarter | Objective | Key Results | Owner
Q1 2026 | Establish secure compliant AI-augmented threat intelligence processing infrastructure with local LLM deployment achieving 90% extraction accuracy | • Deploy local LLM infrastructure processing 250 daily threat feeds with 95% uptime • Achieve 90% threat extraction accuracy on pilot dataset of 10000 threat documents • Complete security assessment and compliance validation for India/Singapore regulations • Reduce manual processing time by 40 hours/week through automated extraction | Security Lead, Infrastructure Lead, AI Engineering Lead, Operations Manager
Q1 2026 | Implement comprehensive compliance and security controls ensuring 100% regulatory adherence across India and Singapore jurisdictions | • Achieve 85% compliance audit score across both jurisdictions • Implement complete audit trail covering 100% of data processing activities • Deploy data anonymization reducing PII exposure to zero incidents • Establish retention policies with automated enforcement for both jurisdictions | Privacy Engineer, Compliance Officer, Data Governance Lead, Audit Lead
Q2 2026 | Scale AI processing to 350 daily feeds with 93% accuracy and reduce MTTI to 1.8 hours through advanced classification and auto-scaling | • Scale processing to 350 daily threat feeds (90% coverage) with 97% LLM availability • Improve threat extraction accuracy to 93% and reduce false positives to 12% • Reduce Mean Time to Threat Identification (MTTI) from 2.5 to 1.8 hours • Achieve 80 hours/week analyst time savings through enhanced automation | Infrastructure Lead, SOC Manager, AI Engineering Lead, Operations Manager
Q2 2026 | Deliver high-performance centralized threat intelligence repository with 3-second query response and near real-time updates | • Achieve 3-second query response time for 95% of searches • Implement near real-time updates with <5 minute ingestion lag • Deploy deduplication reducing redundant threats by 70% • Establish confidence scoring with 90% accuracy in threat prioritization | Platform Engineer, Data Engineering Lead, Backend Lead, AI Engineering Lead
Q3 2026 | Achieve 92% compliance audit score with advanced governance controls and automated regulatory change adaptation | • Achieve 92% compliance audit score with zero critical findings • Implement regulatory change adaptation within 15-day SLA • Deploy cross-jurisdictional data lineage tracking for 100% of processing • Reduce compliance review time by 50% through automated reporting | Compliance Operations, Data Governance Lead, Compliance Officer, Regulatory Lead
Q3 2026 | Deploy web-based intelligence dashboard with real-time monitoring and historical analytics supporting 100+ concurrent users | • Launch web dashboard with <3 second load time for 95% of page views • Implement real-time metrics display with <5 second refresh rate • Deploy historical trend analysis covering 12 months of threat data • Support 100+ concurrent users with <2 second response degradation | Performance Engineer, Platform Engineer, Data Analytics Lead, Frontend Lead
Q4 2026 | Achieve 95% threat extraction accuracy <2 second query performance and establish foundation for global expansion | • Achieve 96% threat extraction accuracy with 8% false positive rate • Optimize query performance to <2 seconds for 98% of searches • Reduce MTTI to 45 minutes through advanced automation • Document scalability roadmap supporting 5x data volume growth | Platform Engineer, SOC Manager, AI Engineering Lead, System Architect
Q4 2026 | Establish operational excellence with 150 hours/week analyst time savings and comprehensive knowledge management | • Achieve 150 hours/week analyst time savings (60% reduction in manual effort) • Maintain 99.5% LLM processing availability with <30 minute recovery time • Deploy knowledge management system capturing 100% of threat analysis patterns • Achieve 95% user satisfaction score from SOC and Intelligence teams | Infrastructure Lead, Product Manager, Operations Manager, Knowledge Management Lead
Implementation Plan
Quarter | EPIC | Feature/User Story | Type | Owner | Dependencies
Q1 2026 | EPIC: Establish secure compliant AI-augmented threat intelligence processing infrastructure with local LLM deployment achieving 90% extraction accuracy |  |  | Product Manager
Q1 2026 | Feature: Local LLM Infrastructure Deployment |  | Feature | Infrastructure Lead
Q1 2026 |  | → As a System Administrator I want to deploy local LLM instances within secure bank infrastructure so that sensitive threat data processing remains compliant and within organizational boundaries | User Story | Infrastructure Engineer_1 | nan
Q1 2026 |  | → As a System Administrator I want automated LLM health monitoring and alerting so that I can proactively address infrastructure issues before they impact processing | User Story | Infrastructure Engineer_2 | nan
Q1 2026 |  | → As a Security Administrator I want LLM infrastructure isolated within secure network segments so that threat data never leaves bank's controlled environment | User Story | Security Engineer_1 | nan
Q1 2026 | Feature: Threat Intelligence Processing Pipeline |  | Feature | Engineering Lead_1
Q1 2026 |  | → As a Cyber Intelligence Analyst I want automated threat indicator extraction from unstructured documents so that I can reduce manual analysis time by 40% | User Story | Backend Developer_1 | nan
Q1 2026 |  | → As a Data Engineer I want batch processing scheduler handling 250 daily feeds so that all threat sources are processed within SLA timeframes | User Story | Backend Developer_2 | nan
Q1 2026 |  | → As a Cyber Intelligence Analyst I want structured output in standardized threat intelligence format so that extracted data integrates with existing security tools | User Story | Backend Developer_3 | nan
Q1 2026 | Feature: Data Privacy and Compliance Framework |  | Feature | Compliance Lead
Q1 2026 |  | → As a Compliance Officer I want audit logging and data anonymization controls so that threat processing complies with India/Singapore regulations | User Story | Compliance Engineer_1 | nan
Q1 2026 |  | → As a SOC Analyst I want to query processed threat intelligence with <5 second response time so that I can rapidly assess emerging threats | User Story | Backend Developer_4 | nan
Q1 2026 |  | → As a Data Protection Officer I want automated PII detection in threat data so that sensitive information is identified and protected during processing | User Story | Compliance Engineer_2 | nan
Q1 2026 | EPIC: Implement comprehensive compliance and security controls ensuring 100% regulatory adherence across India and Singapore jurisdictions |  |  | Compliance Manager
Q1 2026 | Feature: Multi-Jurisdiction Compliance Management |  | Feature | Compliance Lead
Q1 2026 |  | → As a Compliance Officer I want jurisdiction-specific data handling rules so that cross-border threat data complies with local regulations | User Story | Compliance Engineer_3 | nan
Q1 2026 |  | → As a Legal Team Member I want separate compliance controls for India and Singapore so that each jurisdiction's requirements are independently managed | User Story | Legal Analyst_1 | nan
Q1 2026 | Feature: Audit Logging and Traceability System |  | Feature | Engineering Lead_2
Q1 2026 |  | → As a Legal Team Member I want complete audit trails for regulatory review so that we can demonstrate compliance during audits | User Story | Backend Developer_5 | nan
Q1 2026 |  | → As an Auditor I want tamper-proof audit logs with timestamps and user attribution so that I can verify all processing activities | User Story | Backend Developer_6 | nan
Q1 2026 | Feature: Data Anonymization and Privacy Controls |  | Feature | Privacy Lead
Q1 2026 |  | → As a Data Protection Officer I want automated PII detection and anonymization so that sensitive data is protected throughout processing | User Story | Privacy Engineer_1 | nan
Q1 2026 |  | → As a Security Administrator I want retention policy enforcement so that threat data is archived or disposed per governance requirements | User Story | Backend Developer_7 | nan
Q2 2026 | EPIC: Scale AI processing to 350 daily feeds with 93% accuracy and reduce MTTI to 1.8 hours through advanced classification and auto-scaling |  |  | Product Manager
Q2 2026 | Feature: Advanced Threat Classification Engine |  | Feature | AI Engineering Lead
Q2 2026 |  | → As a Cyber Intelligence Analyst I want advanced threat classification by type and severity so that I can prioritize high-impact threats effectively | User Story | AI Engineer_1 | nan
Q2 2026 |  | → As a SOC Analyst I want automated threat severity scoring based on context and impact so that I can focus investigation efforts on critical threats | User Story | AI Engineer_2 | nan
Q2 2026 | Feature: Auto-Scaling LLM Processing |  | Feature | Infrastructure Lead
Q2 2026 |  | → As a System Administrator I want auto-scaling LLM instances based on processing demand so that system handles peak loads without manual intervention | User Story | Infrastructure Engineer_3 | nan
Q2 2026 |  | → As a Platform Engineer I want dynamic resource allocation optimizing cost and performance so that infrastructure scales efficiently with workload | User Story | Platform Engineer_1 | nan
Q2 2026 | Feature: False Positive Reduction System |  | Feature | Data Quality Lead
Q2 2026 |  | → As a SOC Analyst I want false positive filtering reducing noise by 50% so that I can focus on genuine threat investigations | User Story | Backend Developer_8 | nan
Q2 2026 |  | → As a Threat Intelligence Manager I want real-time processing metrics so that I can monitor system performance and identify bottlenecks | User Story | Backend Developer_9 | nan
Q2 2026 | EPIC: Deliver high-performance centralized threat intelligence repository with 3-second query response and near real-time updates |  |  | Platform Lead
Q2 2026 | Feature: High-Performance Search and Query Engine |  | Feature | Platform Engineer
Q2 2026 |  | → As a SOC Analyst I want sub-3-second threat intelligence searches so that I can rapidly investigate security incidents | User Story | Backend Developer_10 | nan
Q2 2026 |  | → As a Threat Hunter I want advanced search with boolean operators and filters so that I can construct complex threat queries efficiently | User Story | Backend Developer_11 | nan
Q2 2026 | Feature: Real-Time Data Ingestion Pipeline |  | Feature | Data Engineering Lead
Q2 2026 |  | → As a Security Operations Manager I want deduplicated consolidated threats so that analysts aren't overwhelmed with redundant information | User Story | Data Engineer_1 | nan
Q2 2026 |  | → As a Threat Hunter I want near real-time threat updates so that I can respond to emerging threats within minutes | User Story | Data Engineer_2 | nan
Q2 2026 | Feature: Deduplication and Consolidation Logic |  | Feature | Backend Lead
Q2 2026 |  | → As a Cyber Intelligence Analyst I want confidence-scored threat rankings so that I can prioritize investigation of high-confidence threats | User Story | Backend Developer_12 | nan
Q2 2026 |  | → As a Data Engineer I want automated deduplication identifying similar threats across sources so that repository maintains clean consolidated data | User Story | Backend Developer_13 | nan
Q3 2026 | EPIC: Achieve 92% compliance audit score with advanced governance controls and automated regulatory change adaptation |  |  | Compliance Manager
Q3 2026 | Feature: Regulatory Change Management System |  | Feature | Regulatory Lead
Q3 2026 |  | → As a Compliance Officer I want automated regulatory change detection so that system adapts to new requirements within 15 days | User Story | Compliance Engineer_4 | nan
Q3 2026 |  | → As a Legal Team Member I want regulatory update notifications with impact assessment so that I can plan compliance adaptations proactively | User Story | Legal Analyst_2 | nan
Q3 2026 | Feature: Cross-Jurisdictional Data Lineage Tracking |  | Feature | Data Governance Lead
Q3 2026 |  | → As a Legal Team Member I want complete data lineage across jurisdictions so that we can demonstrate compliance with cross-border data handling | User Story | Backend Developer_14 | nan
Q3 2026 |  | → As an Auditor I want detailed processing history for both jurisdictions so that I can verify compliance during audits | User Story | Backend Developer_15 | nan
Q3 2026 | Feature: Automated Compliance Reporting |  | Feature | Compliance Operations
Q3 2026 |  | → As a Compliance Manager I want automated compliance reports so that regulatory submissions are completed 50% faster | User Story | Compliance Engineer_5 | nan
Q3 2026 |  | → As a Compliance Officer I want scheduled regulatory reports with customizable templates so that I can meet submission deadlines without manual data collection | User Story | Compliance Engineer_6 | nan
Q3 2026 | EPIC: Deploy web-based intelligence dashboard with real-time monitoring and historical analytics supporting 100+ concurrent users |  |  | Frontend Lead
Q3 2026 | Feature: Real-Time Intelligence Dashboard |  | Feature | Frontend Lead
Q3 2026 |  | → As a Threat Intelligence Manager I want real-time processing metrics dashboard so that I can monitor operations and identify issues immediately | User Story | Frontend Developer_1 | nan
Q3 2026 |  | → As a CISO I want executive-level threat intelligence summaries so that I can report security posture to executive leadership | User Story | Frontend Developer_2 | nan
Q3 2026 | Feature: Performance Monitoring and Visualization |  | Feature | Platform Engineer
Q3 2026 |  | → As a SOC Lead I want historical threat trend visualizations so that I can identify patterns and plan defensive strategies | User Story | Frontend Developer_3 | nan
Q3 2026 |  | → As a Security Analyst I want processing queue visibility so that I can understand current system load and expected processing times | User Story | Frontend Developer_4 | nan
Q3 2026 | Feature: Historical Trend Analysis Capabilities |  | Feature | Data Analytics Lead
Q3 2026 |  | → As a Threat Intelligence Analyst I want interactive trend charts showing threat volume over time so that I can identify seasonal patterns and anomalies | User Story | Analytics Engineer_1 | nan
Q3 2026 |  | → As a Security Manager I want comparative analysis across threat types and sources so that I can assess the most critical threat vectors | User Story | Analytics Engineer_2 | nan
Q4 2026 | EPIC: Achieve 95% threat extraction accuracy <2 second query performance and establish foundation for global expansion |  |  | Product Manager
Q4 2026 | Feature: Advanced Threat Correlation Engine |  | Feature | AI Engineering Lead
Q4 2026 |  | → As a Cyber Intelligence Analyst I want automated threat correlation across sources so that I can identify sophisticated multi-stage attacks | User Story | AI Engineer_3 | nan
Q4 2026 |  | → As a Threat Hunter I want relationship mapping between related threats so that I can understand attack campaigns and actor patterns | User Story | AI Engineer_4 | nan
Q4 2026 | Feature: Performance Optimization and Caching |  | Feature | Platform Engineer
Q4 2026 |  | → As a SOC Analyst I want sub-2-second intelligence queries so that incident response is not delayed by data retrieval | User Story | Backend Developer_16 | nan
Q4 2026 |  | → As a Platform Engineer I want intelligent caching reducing database load by 60% so that system maintains performance at scale | User Story | Platform Engineer_2 | nan
Q4 2026 | Feature: Scalability Architecture for Global Expansion |  | Feature | System Architect
Q4 2026 |  | → As a System Architect I want scalability documentation for 5x growth so that platform can expand to additional countries | User Story | Solutions Architect_1 | nan
Q4 2026 |  | → As a Technical Lead I want modular architecture supporting new jurisdictions so that global expansion requires minimal rework | User Story | Solutions Architect_2 | nan
Q4 2026 | EPIC: Establish operational excellence with 150 hours/week analyst time savings and comprehensive knowledge management |  |  | Operations Lead
Q4 2026 | Feature: Analyst Productivity Optimization |  | Feature | Operations Lead
Q4 2026 |  | → As a Cyber Intelligence Analyst I want automated routine analysis tasks so that I can focus on high-value threat hunting | User Story | Backend Developer_17 | nan
Q4 2026 |  | → As a Team Lead I want productivity metrics showing 60% time savings so that I can demonstrate ROI and reallocate resources | User Story | Analytics Engineer_3 | nan
Q4 2026 | Feature: High-Availability Architecture |  | Feature | Infrastructure Lead
Q4 2026 |  | → As a System Administrator I want 99.5% uptime with automated failover so that threat processing is never interrupted | User Story | Infrastructure Engineer_4 | nan
Q4 2026 |  | → As a Platform Engineer I want disaster recovery with <30 minute RTO so that critical threat processing resumes quickly after failures | User Story | Platform Engineer_3 | nan
Q4 2026 | Feature: Threat Intelligence Knowledge Management |  | Feature | Knowledge Management Lead
Q4 2026 |  | → As a Senior Analyst I want knowledge base capturing analysis patterns so that junior analysts can leverage institutional expertise | User Story | Knowledge Engineer_1 | nan
Q4 2026 |  | → As a Training Manager I want searchable knowledge repository with best practices so that new analysts can onboard 50% faster | User Story | Knowledge Engineer_2 | nan
Dependencies
Dependency Type | Description | Risk Level | Mitigation
Internal Dependency | Delays in procuring GPU-enabled servers for local LLM deployment could push Q1 milestone by 4-6 weeks | High | Initiate procurement immediately with expedited vendor selection; consider cloud-based pilot for testing while hardware arrives
Internal Dependency | Security architecture review and approval for LLM integration within secure bank network requires 3-4 weeks | Medium | Engage Security Architecture team in parallel with initial design phase; prepare comprehensive security documentation early
Internal Dependency | Legal/Compliance validation for India/Singapore regulations requires dedicated resource time during Q1 | Medium | Schedule compliance review workshops in advance; prepare detailed compliance documentation for review
Internal Dependency | Technical dependencies on existing CTIP APIs and data formats; integration complexity unknown until technical discovery | Medium | Conduct technical discovery sprint in first 2 weeks; identify integration interfaces early
External Dependency | Coordination with external threat intelligence feed vendors for API access and data format specifications | Low | Establish vendor communication channels early; document API specifications in advance
Internal Dependency | Availability of training team and analyst capacity for user training during Q3-Q4 rollout | Low | Plan training sessions 6 weeks in advance; create self-service training materials
Risks
Risk Type | Description | Risk Level | Mitigation
Technical Risk | Accuracy drops below 90% threshold affecting analyst trust and adoption | High | Implement continuous model monitoring with automated alerts; establish model retraining pipeline with quarterly updates; maintain diverse model ensemble for resilience
Data Risk | Poor quality or inconsistent threat feed data impacts extraction accuracy | High | Implement data quality scoring and validation at ingestion; establish feed quality SLAs with vendors; deploy data normalization and cleansing pipeline
Compliance Risk | New regulations in India/Singapore requiring system modifications during implementation | Medium | Establish regulatory monitoring process with 15-day adaptation SLA; design flexible compliance framework accommodating change; maintain legal/compliance partnership
Capacity Risk | Threat feed volume grows faster than projected (>375 feeds/day) | Medium | Design auto-scaling architecture from Q1; implement processing queue management with priority-based scheduling; establish capacity monitoring with early warning thresholds
Technical Risk | Technical complexity of integrating with existing CTIP infrastructure higher than anticipated | Medium | Conduct comprehensive technical discovery in Sprint 1; establish API abstraction layer for loose coupling; plan phased integration with fallback options
Adoption Risk | Analysts resistant to AI-augmented workflows or skeptical of LLM accuracy | Medium | Implement comprehensive change management program; demonstrate accuracy improvements in pilot; involve analysts in UAT and feedback loops; provide extensive training
Security Risk | Security vulnerabilities discovered in LLM frameworks or dependencies | High | Conduct security assessment before production deployment; implement vulnerability scanning in CI/CD pipeline; establish security patching SLA; maintain isolated network segments
Compliance Risk | Conflicting requirements between India and Singapore data protection laws | Medium | Engage legal experts from both jurisdictions early; design jurisdiction-aware data handling with separate processing pipelines if needed; document legal guidance for edge cases
Performance Risk | System performance degrades below SLA when processing >300 feeds simultaneously | Medium | Conduct load testing starting Q1; implement performance monitoring with automated scaling; optimize database queries and caching; establish performance baselines
Resource Risk | Key team members leaving during implementation causing knowledge gaps | Low | Document architecture and design decisions comprehensively; implement pair programming and knowledge sharing; cross-train team members on critical components
Issues
Category | Item | Description | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Owner
Budget_Issue | GPU_Hardware_Approval | Budget approval for GPU hardware pending; escalate to CFO with business case demonstrating $14M annual value | nan | nan | nan | nan | CFO
Legal_Issue | LLM_Licensing_Review | LLM model licensing terms under legal review; preparing licensing comparison matrix for commercial use decision | nan | nan | nan | nan | Legal Team
Technical_Issue | CTIP_API_Documentation | CTIP API documentation incomplete; schedule knowledge transfer sessions with existing CTIP team | nan | nan | nan | nan | Technical Lead